## Epic Summary
Epic ID | Epic Description | Story Points | Story Count
VDP-447 | O-series Transaction Logs Ingestion | 38.25 | 11
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 46.75 | 12
VDP-513 | O-series Hybrid Ingestion Ops Support | 45.9 | 12
VDP-512 | OSC Monitoring Support | 46.75 | 11
VDP-498 | AI Consumption Tracking | 66.3 | 14
VDP-499 | VVC Data Phase 2 | 42.5 | 11
VDP-496 | Express Returns Data Semantic Layer | 34 | 9
VDP-508 | Connectors & TAICC Data Semantic Layer | 26 | 7
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 57.8 | 14
VDP-387 | VVC Data Ingestion (26S; In Progress) | 42.5 | 11
TOTAL | All 10 Epics | 446.75 | 112

## Story Details
Epic ID | Epic Description | Story # | Story / Activity | Story Points
VDP-447 | O-series Transaction Logs Ingestion | 1 | Requirement analysis and source-team discussions | 2.55
VDP-447 | O-series Transaction Logs Ingestion | 2 | Source assessment for OSC, Classic Cloud, VOD Hybrid and Premier/Max | 4.25
VDP-447 | O-series Transaction Logs Ingestion | 3 | Review existing ingestion architecture and technical design | 2.55
VDP-447 | O-series Transaction Logs Ingestion | 4 | Define RAW layer data models for request/response logs | 4.25
VDP-447 | O-series Transaction Logs Ingestion | 5 | Define Semantic layer models and transformations | 4.25
VDP-447 | O-series Transaction Logs Ingestion | 6 | Configure ingestion framework and source integration contracts | 4.25
VDP-447 | O-series Transaction Logs Ingestion | 7 | Enable self-service ingestion scheduling | 4.25
VDP-447 | O-series Transaction Logs Ingestion | 8 | Implement ingestion status tracking and failure notifications | 2.55
VDP-447 | O-series Transaction Logs Ingestion | 9 | Define historical data loading and reprocessing approach | 2.55
VDP-447 | O-series Transaction Logs Ingestion | 10 | Data validation and integration testing | 4.25
VDP-447 | O-series Transaction Logs Ingestion | 11 | Deployment, documentation and handover | 2.55
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 1 | Requirement analysis and source-team discussions | 2.55
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 2 | Assess AWS and OCI source systems and customer instances | 4.25
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 3 | Review O-series 9.0 architecture and identify reusable components | 2.55
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 4 | Design O-series 8.0 ingestion architecture and source connectivity | 4.25
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 5 | Configure ingestion pipelines for AWS and OCI | 6.8
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 6 | Implement incremental ingestion for insert, update and delete operations | 4.25
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 7 | Implement historical data ingestion and backfill | 4.25
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 8 | Develop RAW layer ingestion and schema mappings | 4.25
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 9 | Map transactional data to existing OSC Invoice Tax Transaction Semantic layer | 4.25
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 10 | Configure customer-specific ingestion scheduling | 2.55
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 11 | Implement data reconciliation, error handling and reprocessing | 2.55
VDP-514 | O-series Hybrid 8.0 Data Ingestion | 12 | Integration testing, deployment and documentation | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 1 | Requirement analysis, existing ingestion process review and source-team coordination | 2.55
VDP-513 | O-series Hybrid Ingestion Ops Support | 2 | Identify opted-in VOD and On-prem customer accounts and validate prerequisites | 2.55
VDP-513 | O-series Hybrid Ingestion Ops Support | 3 | Configure source connectivity, access and ingestion prerequisites | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 4 | Ingest VOD customer configuration data | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 5 | Ingest VOD historical transaction data | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 6 | Configure and execute ongoing VOD transaction ingestion | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 7 | Ingest On-prem customer configuration data | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 8 | Ingest On-prem historical transaction data | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 9 | Configure and execute ongoing On-prem transaction ingestion | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 10 | Automate repeatable ingestion and onboarding activities | 4.25
VDP-513 | O-series Hybrid Ingestion Ops Support | 11 | Implement operational monitoring, failure handling and reconciliation | 2.55
VDP-513 | O-series Hybrid Ingestion Ops Support | 12 | End-to-end validation, documentation and Ops handover | 4.25
VDP-512 | OSC Monitoring Support | 1 | Requirement analysis and coordination with OSC source team | 2.55
VDP-512 | OSC Monitoring Support | 2 | Source assessment, metrics identification, data volume and schema analysis | 4.25
VDP-512 | OSC Monitoring Support | 3 | Architecture and technical design for OSC monitoring ingestion | 4.25
VDP-512 | OSC Monitoring Support | 4 | Infrastructure provisioning and source connectivity | 4.25
VDP-512 | OSC Monitoring Support | 5 | Develop ingestion pipeline for OSC unstructured metrics data | 6.8
VDP-512 | OSC Monitoring Support | 6 | Develop RAW layer data models and storage | 4.25
VDP-512 | OSC Monitoring Support | 7 | Develop Semantic layer transformations for monitoring metrics | 6.8
VDP-512 | OSC Monitoring Support | 8 | Implement data access and expose Semantic layer to OSC | 4.25
VDP-512 | OSC Monitoring Support | 9 | Configure ingestion scheduling, monitoring and error handling | 2.55
VDP-512 | OSC Monitoring Support | 10 | End-to-end testing, data validation and performance testing | 4.25
VDP-512 | OSC Monitoring Support | 11 | Deployment, documentation and knowledge transfer | 2.55
VDP-498 | AI Consumption Tracking | 1 | Requirements analysis and source-team coordination | 2.55
VDP-498 | AI Consumption Tracking | 2 | Salesforce and AI telemetry source assessment | 4.25
VDP-498 | AI Consumption Tracking | 3 | Architecture and technical design | 4.25
VDP-498 | AI Consumption Tracking | 4 | Salesforce contract ingestion pipeline | 4.25
VDP-498 | AI Consumption Tracking | 5 | Contract amendments, renewals and version processing | 4.25
VDP-498 | AI Consumption Tracking | 6 | AI consumption ingestion with incremental/near-real-time support | 6.8
VDP-498 | AI Consumption Tracking | 7 | Duplicate consumption event handling | 4.25
VDP-498 | AI Consumption Tracking | 8 | RAW layer data modeling | 4.25
VDP-498 | AI Consumption Tracking | 9 | Customer, tenant and contract association | 6.8
VDP-498 | AI Consumption Tracking | 10 | Contract effective-date matching and exception handling | 6.8
VDP-498 | AI Consumption Tracking | 11 | Semantic layer development and governance attributes | 6.8
VDP-498 | AI Consumption Tracking | 12 | Entitlement, remaining balance and utilization calculations | 4.25
VDP-498 | AI Consumption Tracking | 13 | Ingestion monitoring and error handling | 2.55
VDP-498 | AI Consumption Tracking | 14 | Integration testing, reconciliation and deployment | 4.25
VDP-499 | VVC Data Phase 2 | 1 | Requirement analysis and coordination with VVC / Express Returns teams | 2.55
VDP-499 | VVC Data Phase 2 | 2 | Source assessment, schema analysis and identification of VVC configuration assets | 4.25
VDP-499 | VVC Data Phase 2 | 3 | Review existing VDP architecture and design source-to-target mappings | 2.55
VDP-499 | VVC Data Phase 2 | 4 | Develop RAW data models for VVC configuration assets | 4.25
VDP-499 | VVC Data Phase 2 | 5 | Develop RAW models for imported tax data and returns output | 4.25
VDP-499 | VVC Data Phase 2 | 6 | Develop standardized Semantic data models and transformations | 6.8
VDP-499 | VVC Data Phase 2 | 7 | Configure ingestion integration and self-service data push capabilities | 4.25
VDP-499 | VVC Data Phase 2 | 8 | Configure daily/weekly scheduling and ingestion status confirmation | 2.55
VDP-499 | VVC Data Phase 2 | 9 | Implement customer entitlement linking and mapping logic | 4.25
VDP-499 | VVC Data Phase 2 | 10 | Implement entitlement mapping validation and data quality checks | 2.55
VDP-499 | VVC Data Phase 2 | 11 | Integration testing, deployment and documentation | 4.25
VDP-496 | Express Returns Data Semantic Layer | 1 | Requirement analysis and coordination with Express Returns source team | 3
VDP-496 | Express Returns Data Semantic Layer | 2 | Source schema assessment and identification of data assets | 5
VDP-496 | Express Returns Data Semantic Layer | 3 | Review existing RAW data models and define source-to-target mappings | 3
VDP-496 | Express Returns Data Semantic Layer | 4 | Develop Semantic models for taxpayers and configured returns | 5
VDP-496 | Express Returns Data Semantic Layer | 5 | Develop Semantic models for application settings and O-series connections | 3
VDP-496 | Express Returns Data Semantic Layer | 6 | Develop Semantic models for tax and operational data | 5
VDP-496 | Express Returns Data Semantic Layer | 7 | Develop Semantic models for returns data assets | 5
VDP-496 | Express Returns Data Semantic Layer | 8 | Apply VDP naming, governance and data quality standards | 2
VDP-496 | Express Returns Data Semantic Layer | 9 | Integration testing, validation, deployment and documentation | 3
VDP-508 | Connectors & TAICC Data Semantic Layer | 1 | Requirement analysis and coordination with Connectors and TAICC source teams | 3
VDP-508 | Connectors & TAICC Data Semantic Layer | 2 | Source schema assessment and identification of data assets | 5
VDP-508 | Connectors & TAICC Data Semantic Layer | 3 | Review existing RAW data models and define source-to-target mappings | 3
VDP-508 | Connectors & TAICC Data Semantic Layer | 4 | Develop Connectors Semantic data models | 5
VDP-508 | Connectors & TAICC Data Semantic Layer | 5 | Develop TAICC Semantic data models | 5
VDP-508 | Connectors & TAICC Data Semantic Layer | 6 | Apply VDP naming, structure and governance standards | 2
VDP-508 | Connectors & TAICC Data Semantic Layer | 7 | Integration testing, validation, deployment and documentation | 3
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 1 | Analyze existing ITT, CTC and Solutions Reporting pipelines, query profiles and Snowflake costs | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 2 | Establish baseline performance, compute usage, refresh latency and success metrics | 2.55
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 3 | Analyze Platform Reporting Dynamic Tables and identify FULL refresh causes | 2.55
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 4 | Design and validate incremental Dynamic Table refresh POC | 6.8
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 5 | Benchmark DT query optimization, warehouse sizing and target lag | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 6 | Analyze ITT MERGE queries, self-joins and partition pruning | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 7 | Design and test ITT split-processing architecture with historical lookback | 6.8
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 8 | Evaluate stored procedure approach with dynamic partition pruning | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 9 | Benchmark ITT alternatives for cost, performance and correctness | 2.55
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 10 | Analyze CTC MERGE processing and implement change-detection POC | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 11 | Evaluate CTC Dynamic Tables and clustering optimization | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 12 | Validate CTC incremental accuracy and benchmark cost reduction | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 13 | Prepare target architecture, phased migration and rollback strategy | 4.25
VDP-509 | ITT, CTC & Solutions Reporting Pipeline Optimizations | 14 | Finalize cross-team validation, technical documentation and production readiness recommendations | 2.55
VDP-387 | VVC Data Ingestion (26S; In Progress) | 1 | Requirement analysis and Express Returns/VVC team coordination | 2.55
VDP-387 | VVC Data Ingestion (26S; In Progress) | 2 | Assess source schemas and inventory VVC configuration, imported tax and returns output assets | 4.25
VDP-387 | VVC Data Ingestion (26S; In Progress) | 3 | Review existing VDP architecture and source-to-target mapping | 2.55
VDP-387 | VVC Data Ingestion (26S; In Progress) | 4 | Define RAW models for VVC configuration assets | 4.25
VDP-387 | VVC Data Ingestion (26S; In Progress) | 5 | Define RAW models for imported tax data and returns output | 4.25
VDP-387 | VVC Data Ingestion (26S; In Progress) | 6 | Develop standardized Semantic data models and transformations | 6.8
VDP-387 | VVC Data Ingestion (26S; In Progress) | 7 | Enable integration contracts and self-service data push | 4.25
VDP-387 | VVC Data Ingestion (26S; In Progress) | 8 | Configure daily/weekly schedules and ingestion success confirmation | 2.55
VDP-387 | VVC Data Ingestion (26S; In Progress) | 9 | Implement customer entitlement association and mapping | 4.25
VDP-387 | VVC Data Ingestion (26S; In Progress) | 10 | Validate entitlement accuracy, data quality and downstream readiness | 2.55
VDP-387 | VVC Data Ingestion (26S; In Progress) | 11 | Integration testing, deployment documentation and handover | 4.25

## Assumptions
Topic | Assumption / Note
Scope | Planning estimates are subject to backlog refinement and source-team confirmation.
Story point scale | Decimal story points are planning values; align with team estimation conventions before entering Jira.
VDP-387 / VDP-499 | VVC scope substantially overlaps; confirm remaining work to avoid double counting.
VDP-387 | In Progress; estimate represents full scope rather than confirmed remaining work.
VDP-447 | Product team owns actual ingestion execution; VDP scope should be confirmed.
VDP-514 | Confirm O-series 9.0 architecture reuse and configuration-data scope.
VDP-513 | Review overlap with VDP-514.
VDP-512 | Dashboard and alert UI development excluded.
VDP-498 | Billing conversion and automated entitlement enforcement excluded.
VDP-499 | Actual ingestion owned by Express Returns team.
VDP-496 | Semantic layer development; ingestion excluded.
VDP-508 | Semantic layer development; ingestion excluded.
VDP-509 | Design, proof of concept, benchmarking and rollout planning; full production migration excluded.